## Event RACI
Event responsibility matrix
Event / venue |  |  | Plan version |  |  | Reviewed by
Role names → |  | Event lead | Operations | Venue | Safety | Ticketing | Comms | Suppliers
Phase | Task or decision | Event lead | Operations | Venue | Safety | Ticketing | Comms | Suppliers | Assignment check | Handover / evidence link
Planning | Approve event scope and operating plan | [7 empty] | Assign A
Planning | Confirm site map and capacity basis | [7 empty] | Assign A
Planning | Agree permits and venue conditions | [7 empty] | Assign A
Planning | Approve ticket inventory and sales dates | [7 empty] | Assign A
Planning | Approve public event information | [7 empty] | Assign A
Build | Confirm supplier access and load-in sequence | [7 empty] | Assign A
Build | Check temporary layout against approved plan | [7 empty] | Assign A
Opening | Confirm gates and staffing ready | [7 empty] | Assign A
Live | Monitor crowd zones and escalate concerns | [7 empty] | Assign A
Live | Approve operational changes or show pause | [7 empty] | Assign A
Live | Publish attendee changes | [7 empty] | Assign A
Live | Resolve ticketing exceptions | [7 empty] | Assign A
Live | Coordinate medical or emergency interface | [7 empty] | Assign A
Close | Confirm exit and dispersal complete | [7 empty] | Assign A
Close | Record incidents and open follow-ups | [7 empty] | Assign A
Review | Approve debrief actions and owners | [7 empty] | Assign A
R = does the work · A = one accountable decision owner · AR = both · C = consulted before decision · I = informed after decision
Edit role names in row 5. Fill each task using the dropdown; resolve every assignment check before briefing the team.
Example tasks are prompts, not assignments. Adapt workstreams, roles and decisions to the venue and contracts.